## Roles and Responsibilities
Walker Family Reunion Team - Roles and Responsibilities
Team | Team Leader | Team Size | Function | Responsibilities
Core Team
President (Project Manager) | Otis Debnam III | 1 | Oversees the planning of the Walker Family Reunion. | The President shall attend all corporate and team leaders' meeting. The President shall facilitate discussions using the agenda and follow up with team leaders on the status of tasks with upcoming deadlines. In addition, the leader will issue agendas for upcoming meetings. Lastly, the President ensures that all teams are on track with hitting all milestones. In all, the President is responsible to ensure that the WFR is a success. | ·
Vice President | Carla Briggs | 1 | TBD | Lead the group in the vision set forth. Assist the President with duties that the president is responsible for. Providing direction and guidance for the group. Additional responsibilities to be added as necessary.
Executive Assistant | Safiya Kinch | 1 | Assists the President and Vice President
Financial Officer | Wayne Twymon Sr. | 1 | Oversees and manages the finances. | Attends all corporate and team leaders' meetings to ensure all planning aspects align with finances. These responsibilies may also include recommending fundraising goals for activities established by the committee and record all spending and revenue. The leader is responsible for lending financial recommendations. The leader will provide reports on finances, receive all payments, make bank deposits, write checks, and pay all approved expenses.
Secretary | TBD | 1 | Creates Agendas for all meetings and records meeting minutes. | The Secretary is responsible for the following: · Attends all corporate meetings. · Distributes meeting minutes to the appropriate individuals · Manages the database of attendees for registration · Reads the meeting minutes from the previous meeting · Records the meeting minutes at the meetings
Team Leaders | Listed Below |  | Represent respective teams at corporate team meetings | Report results of team activites and leads the team
Liason | TBD | 1 | Works with Committee to communicate information about the WFR to other chapters. | Informs the Committee of things to be shared on social media platforms and on the website in a timely manner.
Team 2
T-Shirt | TBD | 2 | Plans and coordinates the ordering and distribution of the T-shirts. Host the merch table. | Creates the design that will be on the back of the t-shirt, and establishes the color of the t-shirt. Identifies vendors to print the t-shirt, negotiates pricing, ensures the right quantity and variations of sizes are received. The team leader is the primary contact person for all communications with the t-shirt vendor.
Team 3
Entertainment | TBD | 1 to 2 | Plans and coordinates the music for the cookout and secures multimedia equipment | Responsible for securing the DJ for the cookout. This task includes negotiating the fee for service, contract details (arrival time and duration) and ensures the DJ plays appropriate music. This individual works with the hosting location on needs for microphones, projector screens, lcd projector, excellent sound system. The team leader is the primary contact person for all communications with the DJ.
Picnic/ Catering (Optional) | Safiya Kinch / Otis Debnam III. | 4 to 6 | Plans and coordinates the picnic. | Research and identifies location for the picnic and catering services. Reports findings and recommendations to the the activity team. The team leader is the primary contact person for all communications with the picnic site contact and the catering services.
Activities | TBD | 2 to 3 | Plans and coordinates the activities for the WFR. | This team will identify, create and manage activities for the adults and children. They are responsible for recruiting volunteers to run activities as needed. This team will identify and produce a "list of things to see and do" around the area.
Team 5
Registration | TBD | 4 to 6 | Manages and coordinates the registration process at cookout. | This team ensures the following: · Registration table area is setup well in advance of the arrival of the attendees · Creates greeter signs and ensure they are properly displayed · Ensures there is an adequate number of volunteers at the table · Checks in attendees · Distributes badges and family bags · Cleans up and removes any items from the registration area · Works closely with the promotional products and the t-shirt teams.
Historian | Stephen Walker | 2 | Finds and records family history. | TBD
Miscellaneous Resources |  |  | Website
Family Tree
Not in Use
Banquet | Not in Use | 2 to 4 | Plans and coordinates events for the banquet | This team is responsible for coordinating the events for the banquet in addition to working with the booklet team to produce the programs. In addition, this team is responsible for the recognition and acknowledgments at the banquet which includes: achievements, accomplishments, memorials; determines what types of awards i.e., plaques or certificates should be given.
Program Booklet | Not in Use | 2 | Manages the development and production of the program booklet. | Coordinates the design and layout of the program booklet; ensures its accuracy and that all pieces are included; identifies cost effective vendor; ensures the delivery of the programs; works closely with the project team and activities team leaders.
Hotel | Not in Use | 1 | Researches, identifies, makes recommendations for hotels. | This team leader is responsible for visiting hotels, to ensure that it meets the criteria for the needs of the WFR and negotiates room and food prices. This team leader should build and sustains a relationship with the hotel event planner of the selected hotel. The team leader is the primary contact person for communications with the hotel and works closely with the team leaders for the banquet and registration. In addition, this member ensures food selections meets all dietary needs and is responsible for submitting the final food count/selections. The team leader is the primary contact person for all communications with the vendor.
Fundraising | Not in Use | 6 to 8 | Plans and coordinates fundraising activities to help defray costs of the WFR. | Gathers and implements sustainable ideas to raise funds; establishes realistic fundraising goals, the team leader holds the fund raisers accountable to their commitments; collects all the funds; submits the funds to the treasurer in a timely manner, keeps a record of progress made.
Hospitality | Not in Use | 4 to 6 | Plans, coordinates and manages the hospitability event at the hotel. | The teams ensures the following: · Decides on the refreshments to be served · Ensures theres ia an adequate amount of food · Provides paper goods · Ensures that the refreshments are delivered and setup in a timely manner · Greeters are stationed to greet the attendees · Clean the room at the close of the event